| Blackhorse Primary School | Action Plan for English | 2016-17 |
| --- | --- | --- |

| Golden Threads... |  |
| --- | --- |
| Standards | 1. Improve writing (& especially Phonics & Spelling). |
|  | 2. Review Feedback to ensure maximum impact. |
|  | 3. Purposeful Practise to embed key skills. |
| Inclusion | 4. Vulnerable pupils – closing the attainment gap. |
| Curriculum | 5. Develop music and the performing arts. |
| Teaching & Learning | 5. Teacher support – improve % of Outstanding teaching through improving subject knowledge & sharing good practice. |

| Key Strategies/ Actions | Success Criteria (must be precise and measureable). |
| --- | --- |
| Reading: 1. Improve teacher subject knowledge (higher reading skills). 2. Staff using Thinking Hats approach to improve teaching of higher reading skills 3. To improve reading by achieving Bronze award for ‘Time 4 Reading’ by Oct 2016 | - 80% of children achieve or exceed ARE in Reading. - 40% of children make better than expected progress. - End of KS Tests rank BH in top 3 NEXUS schools. - Bronze Time 4 reading award achieved - evidencing increased reading of challenging texts throughout school |
| Writing: 1. Increase teacher subject knowledge of new curriculum. 2. Develop teachers’ writing moderation skills. 2. Teachers increase opportunities for editing and redrafting | - 75% of Y1-5 children are Secure in Writing AREs. - 90% of Y6 achieve interim writing standard. - 50% of children make better than expected progress. - End of KS Tests rank BH in top 3 NEXUS schools. - Opportunities within each unit to edit and redraft (evidenced through ‘purple polishing pen’). |
| Phonics/ Spelling: 1. KS1 phonics: adopt Mangotsfield system and track progress (take part in Phonics Partnership project). 2. Improve spelling teaching in KS2 through CPD. 3. Opportunities for purposeful practise given in Basic Skills sessions. | - 85% of chn to pass Y1 phonics screening and 90% Y2 Re-sit. - 85% of children in KS2 can correctly spell NC work lists. |
| Handwriting: 1. Re-visit cursive handwriting style to ensure that it is correctly taught in every class, especially correct pencil grip & posture. 2. Opportunities for purposeful practise given in basic skills sessions. | - Correct pencil grip to be used by all by end of Term 2 in Year 1 - All staff to be modelling cursive handwriting when writing on boards, displays, marking etc. - Evidence of consistent handwriting style throughout the school and joining by end of EYFS. |

| Blackhorse Primary School |  |  | Action Plan for English |  | 2016-17 |
| --- | --- | --- | --- | --- | --- |
|  | Actions | Led by | Resources Required (incl. time) | What evidence will you collect to show that this has been successfully implemented? | Monitoring Activities (incl. Dates) |
| September | - KS2 Reading: analysis of 2016 papers to look for weaknesses and how to overcome these - Time 4 Reading Bronze award - KS1 staff to visit Mangotsfield to look at phonics teaching in KS1 - Check cursive handwriting is being used throughout the year - English book scrutiny | GB/NF GB/JB/JG JB GB/JB/JG GB/JB | Thurs pm (GB already out, NF free?) JG needs an hour to check reading records JB, AS, EF and SP to visit Mangotsfield N/A JB and GB already out | - Data analysis - Actions for addressing weaknesses - Remind staff to record reading at home (JG to check) - JB and GB to set up parent reading group - Planning and lessons show new approach to teaching - Books and classroom environment show evidence of cursive handwriting - Feedback to staff and governors | - PoR scrutiny which follows weakness handout in SM to focus on these areas- Nov 16 - Bronze award achieved- Oct 16 - JB to termly analyse phonics data and hold PPM meetings specifically for phonics - Monthly - 30.09.16 |
| October | - Thinking Hats staff meeting (moved to 2017-2018) - Marking policy (moved to T3 SLT/inset?)and English weekly planning structure (including mapping out ARE progression) staff meeting | GB/JB GB/JB | Staff meeting (30mins) First week of Oct preferably Staff meeting (19.10.16) | - Evidence of Thinking Hats being used across the curriculum in planning and books - Staff’s planning and books will show discrete SPAG focus teaching on Mon, apply all week to short burst writing and then final show off in Friday’s VCOP and Big Write - Books will show a marking policy agreed in staff meeting | - Book scrutinies show evidence of Thinking Hats activities- Nov 16 - Book and planning scrutiny –Nov 16? moved to Friday 5th May because we had English x2 and PoR scrutinies. |
| November | - Editing and redrafting training - Power of Reading book scrutiny - English planning and book scrutiny - Liase with Vicky Gordon for a list of schools with high percentage of GDS. Visit these schools to look at books, planning and teaching | GB/JB/JG GB GB and JB GB | Staff meeting Already out Leadership time Time out to visit schools | - Evidence of staff using editing and redrafting skills within each unit - Feedback to staff and governors - Feedback to staff and governors - Feedback from schools | - Book scrutinies show evidence of editing and redrafting - 04.11.16 11.11.16 Book scrutinies show evidence of new SPaG teaching structure-(This is booked in for Jan 2017) Jo and Neil have attended GD training as part of ‘The Year of Writing’ (Nov). |
| December | - Apply for Bronze Time 4 Reading - Send out a letter about Adult book club to see how many are interested | GB JB/GB | N/A N/A | - Evidence of criteria met and the award - Responses from parents | - JG monitored reading at home N/A |
| January | - English planning scrutiny | JB/GB | Already out | - Staff’s planning and books will show discrete SPAG focus teaching on Mon, apply all week to short burst writing and then final show off in Friday’s VCOP and Big Write | - Book and planning scrutiny (13.01.17) |
| February | - Thinking Hats staff meeting training & train staff on Interim Framework - Apply for Silver Time 4 Reading - Year 1 phonics monitoring (compare with NEXUS to see if they are inline) | GB/JB GB/JB/JG | Staff meeting May need time out but cannot explicitly say when yet | - Evidence of Thinking Hats being used across the curriculum in planning and books - Year 1&5 to introduce to middle-high attainers in Term 5? - Evidence of criteria met and the award | - Book scrutinies show evidence of Thinking Hats activities |
| March | - World Book Day |  |  |  |  |
| April | - Y6 meet with Claire Ridsdale for drop-in scrutiny to check Greater Depth writers |  |  |  |  |
| May | - Year 1 & 5 launch WTS from Interim Frameworks | GB and JB | GB wed pm out of class (5th April) JB out of class (25th April) | - Books from year groups | - Book and planning scrutiny |
| June |  |  |  |  |  |
| July | - Keep Y1&5 books for WTS evidence |  |  |  |  |