## Sheet1
2024-25 RAP
Term 1 | Wk1: 2.9.24 | Wk 2: 9.9.24 | Wk 3: 16.9.24 | Wk 4: 23.9.24 | Wk 5: 30.9.24 | Wk 6: 7.10.24 | Wk 7: 14:10.24 | Wk 8: 21.10.24 | T1 and T2 Priority Milestones: | T1 Impact
Priority 1: Vision - Further embed a culture of high expectations and challnege so that pupils deomnstrate high levels of resilience and intrinsic motivation |  | Targetted Childrren for Clubs NF/SY to create a list of persitently absent children form 23-24 and begin targetting straegy | Create EYFS Guide to School MIssion (SB/SY/NF) Create Attendance Strategy (JT/NF) | Parent Vision re-launch (SB) | Leaf INSET 1: Distinctly Primary Day 1 (morning) / TA Conference 4.10.24 EYFS Intake 1 | Mark Rowland - Disadvantaged Conference 9.10. |  | Review Pupil Premium Strategy | Parent MIssion Leaders Created 1A Re-launch Mission with Parents (whole school meetings, incl. Pupil Mission Masters). Create ToR for Mission Masters Parents’ group and establish group. 1B: Routines: Codify routines for movement and transitions (incl. ‘why’) staff trained. 1B Lunchtimes: Develop new approach to lunchtime provision. 1B: Peer Critique: Complete staff training on purpose and rationale for peer critique & introduce for presentation. PGP to read research on Peer Critique Ethic of Excellent in Action book club). 1B TLaC: 1C: Participation: Staff trained on Leaf Model for Disadvantage (champion/ Privilege Disadvantage/ Individual empathy) at INSET 1. 1D Attendance: Staff trained on first engagement with parents. Engage with the new DfE Attendance strategy. Target children who were persistently absent in 2023-24 for attendance process. Target 90-95% group to analyse barriers to attendance. School makes the case for good attendance (comms and advertising Eduprise). Engage parents with attendance guide.
Priority 2: Writing - Further develop the teaching of writing so that more children meet or exceed the expected standard |  | Prep for handwriting and Spelling (AP) | Learning Walk - Phonics (AP) 19.9.24 |  |  | Review Writing Policy |  |  | Fidelity: • All teachers are using live modelling throughout the teaching sequence • EYFS and Y1 teachers are beginning to use a codified approach to the teaching of transcription skills Acceptability: • EYFS and Y1 teachers understand the importance of transcriptional skills ahead of compositional skills • Staff understand the importance of live modelling Reach: • Pupils in EYFS and Y1 are being taught through a codified approach to transcription • All children are experiencing live modelling in their writing lessons
Priority 3: Curriculum - Refine the remaining foundation subjects so that pupils can retain, recall and apply knowledge across all subjects. | Maths - Numbots Incentives, Tracking to launch at Meet the Teacher (JDC) Create school plan overview for school year including places of worship NF SB JT | SB to collate Digital Safety Parents Group |  | Sports Premium Plan Music Development Plan |  | Hold DIgital Parents E-safety Meeting | Music Development Plan meeting 2 | Music: Advertise Christmas Choir. SATS Question Level data analysis - Maths (JDC) | End of term 2 Fidelity: • Teachers across both schools trying to plan Music and D.T. sessions using new schemes. Acceptability: • All teachers use slide decks to plan and teach RE. • Teachers are using assessment (concept cartoons, pupil voice) activities to assess History, Science and Geography. Milestone: • Music and DT. progression maps created. • Skeleton plans for DT will be created ready for terms 3 and 4. • RE places of worship/ visitors mapped into the knowledge development document.
School Improvement Priority 1B: Disadvantaged children make the same progress as their peers in maths | [5 empty] | Mark Rowland - Disadvantaged Conference 9.10. |  |  | Short term: End of Term 2 1) Progression of Number Facts created BH Research approaches to closing gaps – LEAF Maths Network 2) Teachers will have access to a clear and consistent vocabulary progression with contains definitions Flashcards for Wider Curriculum being used by all 3) Parents will attend open morning and develop better understanding of supporting their children in mathematics Progression document (end-of-unit outcome for Term 3-5) 4) STEM opportunities have been identified, researched and allocated 5) Mighty Mathematicians identified and trained. 6) Parent STEM Slide completed
MAINTAINING / EMBEDDING/INCLUSION ACTIONS: | SEND Report to Governors | Sports Premium on Website 10/09 Ward round on learning behaviours - how have children settled? |  | Instructional Coaching:Live Modelling | Instructional Coaching: Live Modelling | Ward Round - learning behaviours | Instructional Coaching: Live Modelling
DATA/ PM/ PPM TASKS: |  |  |  |  | SEND SURGERIES (JT/CD) Performance Management Meetings begin | Pm Meetings for teachers | PM meetings for teachers |  | Maths retrieval slide format created
STAFF MEETINGS | Performance Management @EG + Instructional Coaching | Meet the teacher (including slide on Mission and Values linked to Year group) | Spelling and Handwriting (BH) | Attendance and Engaging Vulnerable Children (Clubs) @BH (SB) Leaf Disadvantaged Model | Professional Growth Project - Peer Critque Training | Prep for PM Meetings | TTRS Refresher | Parents Evening
SLT MEETINGS | Staff Handbook/Agree instructional Coaching teams | Empty Classroom Environment Check Leaf Target Setting | Book Look - handwriting and presentation |  |  |  | Complete Target Setting Leaf
LEAF Governance |  | FGB 9.9.24 @ 6:15pm | BH Governor Develpoment Day (18.9) | Safeguarding Governor Visit (Sam Evans)
Term 2 | Wk 1: 4.11.24 | Wk 2: 11.11.24 | Wk 3: 18.11.24 | Wk 4: 25.11.24 Memory Week | Wk 5: 2.12.24 Assessment Week | Wk 6: 9.12.24 | Wk 7: 16.12.24 Wider Curriculum Assessment |  | T2 Priority Milestones: | T2 Impact
Priority 1: Vision - Further embed a culture of high expectations and challenge so that pupils deomnstrate high levels of resilience and intrinsic motivation | JT - Review behaviour expectations with SLT. Lunchtime Routines and expectation monitoring (JT/SB/NF) | EYFS Intake 2 Pupil conferencing: lunchtime expectations and routines Attendence monitoring plan completed | JT - Review corridor transitions around school and possible reasons for inconsistencies. Review lunchtime behaviours in dining hall. Introduce new playtime routine Assembly Tuesday, start Wednesday. | Draft Plan for behaviour and routine (playtime) launch to school | Plan to meet with LBS to launch new Lunchtime behaviours/routine at start of T3. |  |  |  | Parent MIssion Leaders Created Re-launch Mission with Parents (whole school meetings, incl. Pupil Mission Masters). Create ToR for Mission Masters Parents’ group and establish group. 1B: Routines: Codify routines for movement and transitions (incl. ‘why’) staff trained. 1B Lunchtimes: Develop new approach to lunchtime provision. 1B: Peer Critique: Complete staff training on purpose and rationale for peer critique & introduce for presentation. PGP to read research on Peer Critique Ethic of Excellent in Action book club). 1B TLaC: Agree with teaching staff which 2 Means of Participation (MoP) to focus on first. Staff all given laminated visuals for each MoP to display on boards outside classroom and in classroom. TAs trained on TLaC techniques (KU – Sept INSET?) MoP focus in ward rounds (2 of the 5). 1C: Participation: Staff trained on Leaf Model for Disadvantage (champion/ Privilege Disadvantage/ Individual empathy) at INSET 1. 1D Attendance: Staff trained on first engagement with parents. Engage with the new DfE Attendance strategy. Target children who were persistently absent in 2023-24 for attendance process. Target 90-95% group to analyse barriers to attendance. School makes the case for good attendance (comms and advertising Eduprise). Engage parents with attendance guide. | Short Term: End of term 2 1A Vision: Parents / Governors groups established to support school vision. 1B Routines: Children demonstrate agreed ‘Teach Like a Champion’ routines during ward rounds. Pupils begin peer critique of presentation. Vulnerable pupils are prioritised in PPMs through focusing on combined RWM measures. 1C Participation: Vulnerable children have articulated barriers and requests for extra-curricular activities. Vulnerable children prioritised for leadership roles. 1E Attendance: Children who were persistently absent in 2023-24 show this is no longer the case, or attendance process is well advanced.
Priority 2: Writing - Further develop the teaching of writing so that more children meet or exceed the expected standard | Writing Update (SB,GL,LJ) Instructional Coaching - Live Modelling | Instructional Coaching - Live Modelling | Leaf Moderation Support training with Claire Risdale Instructional Coaching - Live Modelling | Instructional Coaching - Live Modelling | Live Modelling Partnership Writing Ward Round (Tues 3rd) | Instructional Coaching - Live Modelling |  |  | Fidelity: • All teachers are using live modelling throughout the teaching sequence • EYFS and Y1 teachers are beginning to use a codified approach to the teaching of transcription skills Acceptability: • EYFS and Y1 teachers understand the importance of transcriptional skills ahead of compositional skills • Staff understand the importance of live modelling Reach: • Pupils in EYFS and Y1 are being taught through a codified approach to transcription • All children are experiencing live modelling in their writing lessons | Short Term: End of term 2 Pupils can talk about the format of different genres of non-fiction writing. Pupils in EYFS and Y1 are being taught through a codified approach to transcription and are having opportunities to practice these key skills. Pupils are experiencing quality first teaching of writing through live modelling and working walls.
Priority 3: Curriculum - Refine the remaining foundation subjects so that pupils can retain, recall and apply knowledge across all subjects. | Art Leader handover LJ/RD 7/11 | PE: MM and LB to write PE action plan 14/11 Wider Curriculum Pupil Conference T1 knowledge Geography & History governor update | Music: Adapt GSfM units to match our approach and create vocab list Finish annual planner incl performance opps Computing: T6 & T1 pupil conference and book look 22/11 MS Science: T6 and T1 pupil conference and book look 18/11 EC DT Action plan writing RW/JT 20/11 | Music: plan Recorder training for staff. Purchase recorders. (SB/SP 25.11) | RE: Produce T3 skeleton plans 5/12 BV | PE: Begin to write slide decks for T3 MM 12/12 History/Geog: Pupil Conference & Book Look T6 and T1 12/12 KU & RW | Staff to complete wider curriculum assessment |  | End of term 2 Fidelity: • Teachers across both schools trying to plan Music and D.T. sessions using new schemes. Acceptability: • All teachers use slide decks to plan and teach RE. • Teachers are using assessment (concept cartoons, pupil voice) activities to assess History, Science and Geography. Milestone: • Music and DT. progression maps created. • Skeleton plans for DT will be created ready for terms 3 and 4. • RE places of worship/ visitors mapped into the knowledge development document. | Short Term: End of term 2 3A Pupils are accessing high quality RE and PE lessons which are clearly mapped and follow the codified approach. 3A Teachers are using key knowledge development documents to plan and deliver Music and DT lessons. 3A The codified slide deck is used in RE teaching to support consistency and metacognition. 3B Places of worship are planned into the knowledge development document for RE. 3B Knowledge notes have been introduced to support the retention of key vocabulary and core knowledge. 3B Assessment is used so pupils experience more lessons matched to their current understanding. 3B Spaced retrieval is being used consistently across classes to ensure children know more and remember more.
School Improvement Priority 1B: Disadvantaged children make the same progress as their peers in maths | Maths ward round - first look. Maths routines. | Pupil conference around flash cards |  | Planning look - reasoning questions. |  | Pattern searching through whole school data for areas of priority. |  |  | Short term: End of Term 2 1) Progression of Number Facts created BH Research approaches to closing gaps – LEAF Maths Network 2) Teachers will have access to a clear and consistent vocabulary progression with contains definitions Flashcards for being used by all 3) Parents will attend open morning and develop better understanding of supporting their children in mathematics Progression document (end-of-unit outcome for Term 3-5) 4) STEM opportunities have been identified, researched and allocated 5) Mighty Mathematicians identified and trained. 6) Parent STEM Slide completed | 1) Increase in percentage children accessing and using TTRS/Numbots, especially disadvantaged children 2) Pupils are experiencing precise mathematical vocabulary in lessons, Pupils will be using Maths Flashcards to recall and retrieve wider mathematical facts 4) Mighty Mathematicians established
MAINTAINING / EMBEDDING ACTIONS: | Reading leads to meet lowest 20% 7/11 |  |  | Reading Ward Round - Reading Routines and engagement 27/11
DATA/ PM/ PPM TASKS: |  |  |  | Memory Week | Assessment Week |  | PPMs
EVENTS/ HR/ SITE:
STAFF MEETINGS | Non-Fiction Writing Writing to Inform EG | Non-Fiction writing Writing to Argue BH | Leaf Trust Staffmeeting (1/5) | Behaviour & routines | Writing Moderation | Non Fiction writing Writing to Explain (EYFS/Y1 with EG | PGP BH (moved to T3)
SLT MEETINGS | JT to lead discussion on behaviour expectations around school re. transitions. |  |  | Book Look - Disadvantaged first 20% English, Maths and Wider Curriculum | RAP review | Book Look - Handwriting, Presentation & RE
LEAF Governance |  | FGB 11.11.24 @ 6:15pm
Term 3 | Wk 1:6.1.25 | Wk 2: 13.1.25 | Wk 3: 20.1.25 Memory Week | Wk 4: 27.1.25 | Wk 5: 3.2.25 | Wk 6: 10.2.25 School opening Anniversary Week |  |  | T4 Priority Milestones: | T3 Impact
Priority 1: Vision - Further embed a culture of high expectations and challnege so that pupils deomnstrate high levels of resilience and intrinsic motivation | EYFS Intake 3 |  | Leaf Trust Staff Meetings (2 of 5) Revamped Parents' Forum Extensive Opportunities | Happiness Survey Follow up Y5/6 complete |  | Distinctly Primary Day 2 (morning) / Admin & Site Conference Happiness survey follow up Y3/4 |  |  | End of term 4 1A Parent Mission Leaders meetings taking place and suggestions enacted and fed back to parents (communication, access to school etc). 1B: Re-launch lunchtime provision. 1B TLaC: Create guidance for T&L Handbook. All 5 MoP now in use. Staff display visuals in classrooms/corridor boards and use icons on slides. Ward rounds show that TLaC techniques are used in all classes. 1B Peer Critique: Trail peer critique in PE and English (YR-1, Y2-4, Y5-6). Create guidance for T&L Handbook. 1D Attendance: Parent/ Pupil Mission Masters engage in campaign to improve attendance. | Medium Term: End of term 4 1A Vision: Parents groups actively engaged in supporting the school mission. 1B Routines: New Teach like a Champion Routines are beginning to be used by children across the school. Pupils begin peer critique PE & English. Attainment: PPMs show that the number of children not on track for EXS in RWM has decreased. 1C Participation: 80% of vulnerable children in KS2 attend clubs. 1D Attendance: Attendance data shows that attendance is improving in previously persistently absent children.
Priority 2: Writing - Further develop the teaching of writing so that more children meet or exceed the expected standard | SM Cohesive Devices in Non-fiction Writing EG | Extended ward round: Live modelling 15.1 & 16.1 | Extended ward round: Live modelling 22.1 | Codify use of peer critique in Edit/ Re-draft | SM Oracy into Writing (levels of formality in NF) EG |  |  |  | End of term 4 Fidelity: • All teachers are using live modelling throughout the teaching sequence • All teachers are teaching non-fiction outcomes linked to progression document • All teachers are using oracy as part of the teaching sequence for writing Acceptability: • EYFS and Y1 teachers are confident in using the updated teaching sequence to ensure children are practicing their transcriptional skills • Teachers are confident in the use of live modelling throughout the teaching sequence • Teachers understand the importance of oracy and how oracy skills support children in their writing Reach: • Y6 pupils are being provided with regularly opportunities to revise and improve their writing. • Pupils in EYFS and Y1 are practicing their transcriptional skills through deliberate, codified teaching | Oral rehearsal of writing is embedded in all year groups, both before and after writing, improving first drafts and revisions. Pupils can talk about the purpose, audience and form of different types of non-fiction writing, and this is starting to show in their independent writing.
Priority 3: Curriculum - Refine the remaining foundation subjects so that pupils can retain, recall and apply knowledge across all subjects. | INSET: Launch recorder initiative. SP to plan Lesson 1 of recorders Y3-6. INSET: DT PLanning for T3 & 4 units and vocabulary | Music: Begin Recorder lessons. Y4 Folk workshop. 16/1 AM Pupil History: Conference and Book Look on T6 and T1, T2 units | Music Complete skeleton plans for T4 SB spending morning in EYFS 21.1 SLT to check vocab of privileged three PE: 23/1 Meg and Lucy to meet to action plan PE Instructional Coaching Tlac techniques in action | Science: 30/1 Pupil Conference and Book Look. RE Skeleton Planning | Instructional Coaching: Tlac techniques 6/2 Computing Pupil Conference | Music: Recorder lesson structure. |  |  | End of term 4 Fidelity: - Lesson structures are codified across different phases. (Principles of Expert Tuition) in DT and Music - Teachers use assessment across the wider curriculum to identify and target gaps - All teachers are creating slide decks for D.T. based on skeleton plans. - All teachers are teaching music lessons demonstrating and teaching musical skills. - Spaced retrieval is used across the curriculum in RE, PE, Music and DT Acceptability: - All teaching staff use the progression maps provided for RE, PE, Music and DT - Some teachers using the assessment models (knowledge notes, concept cartoons, vocabulary) - Subject leaders use information gained from assessment to monitor their subjects and refine approaches - Knowledge notes are in books for History, Science and Geography. Children know this contains key vocabulary and core knowledge. - Some pupils have visited places of worship/visitors from different religious groups have visited school. Milestone: - Skeleton plans written for DT for terms 5 and 6. | Medium Term: End of term 4 Oral rehearsal of writing is embedded in all year groups, both before and after writing, improving first drafts and revisions. Pupils can talk about the purpose, audience and form of different types of non-fiction writing, and this is starting to show in their independent writing.
School Improvement Priority 1B: Disadvantaged children make the same progress as their peers in maths | Mighty mathematicians launch with staff | Mighty Mathematicians used in across school | progression documents (JDC) Meet Caroline about vocab cards | Maths ward round - vocab | 5.2 Gone Green Day Gap planning | Mighty Mathematicians and vocab cards used reviewed |  |  | End of term 4 Medium term: End of Term 4 1) Progression of number facts embedded BH Plan devised to close gaps in arithmetic/fluency 2) Teachers will be explicitly teaching vocabulary in lessons Progression document (end-of-unit outcome Terms 6-2) 3) Teachers to use progression document to help plan and sequence lessons towards end-of-unit outcome 4) Mighty Mathematicians used purposefully | Medium term: End of Term 4 1) Children to be receiving a daily, structured programme of arithmetic fluency. Teachers will identify gaps and responding to them appropriately 2) Teachers to be modelling use of precise vocabulary. Children will be able to apply wider mathematical curriculum facts to their lessons 3) Teachers will using progression document to help sequence lessons and understand end-of-unit goals 4) Disadvantaged pupils will have a more positive attitude towards maths
MAINTAINING / EMBEDDING ACTIONS:
Safeguarding/Wellbeing
DATA/ PM/ PPM TASKS: | PPMs
EVENTS/ HR/ SITE:
STAFF MEETINGS | Cohesive Devices in Non-fiction Writing EG | Plan Anniversary celebration week BH | LEAF Trust Staff Meeting | PGP - Peer Critique in Writing BH | Oracy into Writing (levels of formality in NF) EG | Music: Recorder lesson structure. BH
SLT MEETINGS | Assessment Data
LEAF Governance |  | FGB 13.1.25 @ 6:15pm
Term 4 | Wk 1: 24.2.25 Anniversary Week Showcase | Wk 2: 3.3.25 | Wk 3: 10.3.25 | Wk 4: 17.3.25 - Assessment fortnight | Wk 5: 24.3.25 - Assessment fortnight | Wk 6: 31.3.25 |  |  | T4 Priority Milestones: | T4 Impact
Priority 1: Vision - Further embed a culture of high expectations and challange so that pupils demonstrate high levels of resilience and intrinsic motivation | 26.2 Ward round: TLaC (NF/ SY) TLaC ward round: Talk together (10am EG, 11:15 BH) Codify TLaC Stand & Deliver | Instructional Coaching - TLaC 6/3 KU Plan next stage of PGP and TLAC | Instructional Coaching TLC Engage Misson Leaders on attendance initiatives | 18/3 Parent Mission Forum Instructional Coaching - TLaC Peer Critique - clarify sentence stems and 3 steps. |  | Instructional Coaching - TLaC |  |  | End of term 4 1A Parent Mission Leaders meetings taking place and suggestions enacted and fed back to parents (communication, access to school etc). 1B: Re-launch lunchtime provision. 1B TLaC: Create guidance for T&L Handbook. All 5 MoP now in use. Staff display visuals in classrooms/corridor boards and use icons on slides. Ward rounds show that TLaC techniques are used in all classes. 1B Peer Critique: Trail peer critique in PE and English (YR-1, Y2-4, Y5-6). Create guidance for T&L Handbook. 1D Attendance: Parent/ Pupil Mission Masters engage in campaign to improve attendance. 1B: Re-launch lunchtime provision. 1B TLaC: Create guidance for T&L Handbook. All 5 MoP now in use. Staff display visuals in classrooms/corridor boards and use icons on slides. Ward rounds show that TLaC techniques are used in all classes. 1B Peer Critique: Trail peer critique in PE and English (YR-1, Y2-4, Y5-6). Create guidance for T&L Handbook. 1D Attendance: Parent/ Pupil Mission Masters engage in campaign to improve attendance. | Medium Term: End of term 4 1A Vision: Parents groups actively engaged in supporting the school mission. 1B Routines: New Teach like a Champion Routines are beginning to be used by children across the school. Pupils begin peer critique PE & English. Attainment: PPMs show that the number of children not on track for EXS in RWM has decreased. 1C Participation: 80% of vulnerable children in KS2 attend clubs. 1D Attendance: Attendance data shows that attendance is improving in previously persistently absent children.
Priority 2: Writing - Further develop the teaching of writing so that more children meet or exceed the expected standard |  | Leaf Literature Festival SB to check in Gemma | Leaf Literature Festival SB to check in with Gemma |  | 27.3 Extended Writing Ward Round (both schools) 9am – review SDP to date, 10am EG ward round, 11am BH WR, 12noon summary. |  |  |  | End of term 4 Fidelity: • All teachers are using live modelling throughout the teaching sequence • All teachers are teaching non-fiction outcomes linked to progression document • All teachers are using oracy as part of the teaching sequence for writing Acceptability: • EYFS and Y1 teachers are confident in using the updated teaching sequence to ensure children are practicing their transcriptional skills • Teachers are confident in the use of live modelling throughout the teaching sequence • Teachers understand the importance of oracy and how oracy skills support children in their writing Reach: • Y6 pupils are being provided with regularly opportunities to revise and improve their writing. • Pupils in EYFS and Y1 are practicing their transcriptional skills through deliberate, codified teaching | Oral rehearsal of writing is embedded in all year groups, both before and after writing, improving first drafts and revisions. Pupils can talk about the purpose, audience and form of different types of non-fiction writing, and this is starting to show in their independent writing.
Priority 3: Curriculum - Refine the remaining foundation subjects so that pupils can retain, recall and apply knowledge across all subjects. | 27/2 E-Safety Meeting | 6/3 RW Produce remaining DT skeleton plans | 13/3 BV Produce T5 RE skeleton plans | Music: Y3 Ham Farm Festival performance. | Music: Y2 Flute workshop 27/3 RD Art pupil conferencing |  |  |  | End of term 4 Fidelity: - Lesson structures are codified across different phases. (Principles of Expert Tuition) in DT and Music - Teachers use assessment across the wider curriculum to identify and target gaps - All teachers are creating slide decks for D.T. based on skeleton plans. - All teachers are teaching music lessons demonstrating and teaching musical skills. - Spaced retrieval is used across the curriculum in RE, PE, Music and DT Acceptability: - All teaching staff use the progression maps provided for RE, PE, Music and DT - Some teachers using the assessment models (knowledge notes, concept cartoons, vocabulary) - Subject leaders use information gained from assessment to monitor their subjects and refine approaches - Knowledge notes are in books for History, Science and Geography. Children know this contains key vocabulary and core knowledge. - Some pupils have visited places of worship/visitors from different religious groups have visited school. Milestone: - Skeleton plans written for DT for terms 5 and 6. | Medium Term: End of term 4 Oral rehearsal of writing is embedded in all year groups, both before and after writing, improving first drafts and revisions. Pupils can talk about the purpose, audience and form of different types of non-fiction writing, and this is starting to show in their independent writing.
School Improvement Priority 1B: Disadvantaged children make the same progress as their peers in maths |  | Reorganise Mighty Mathematicians | Share Maths progression document with staff including fluency) | Reorgansie flash cards |  | 31.3 Maths ward round with Kelvin (HT St Helens Alveston) |  |  | End of term 4 Medium term: End of Term 4 1) Progression of number facts embedded BH Plan devised to close gaps in arithmetic/fluency 2) Teachers will be explicitly teaching vocabulary in lessons Progression document (end-of-unit outcome Terms 6-2) 3) Teachers to use progression document to help plan and sequence lessons towards end-of-unit outcome 4) Mighty Mathematicians used purposefully | Medium term: End of Term 4 1) Children to be receiving a daily, structured programme of arithmetic fluency. Teachers will identify gaps and responding to them appropriately 2) Teachers to be modelling use of precise vocabulary. Children will be able to apply wider mathematical curriculum facts to their lessons 3) Teachers will using progression document to help sequence lessons and understand end-of-unit goals 4) Disadvantaged pupils will have a more positive attitude towards maths
MAINTAINING / EMBEDDING ACTIONS: | 26/2 NF/LB meet to plan enrichment 27/2 Reading Subject leads to meet with RIT | 3/3 LA Safeguarding review with Mark Dee
MONITORING: |  |  |  | SEND Review Julia Chapman & Tania Craig | 27/3 BV Phonics ward round
DATA/ PM/ PPM TASKS: | [5 empty] | 3/4 JDC Data tasks for assessment point 2 4/4 Leaf Data drop 2 (Y1-6) Y6 SAT 2024
EVENTS/ HR/ SITE:
STAFF MEETINGS | 25.2 20th Anniversary Celebration Event BH | Writing Exemplification LJ & EC + TLaC & Stop and jot. BH | Trust Staff Meetings (3 of 5) | Mid-Year reports | Parents' Evening | PGP: Peer Critique (unpick 3 steps) EG
SLT MEETINGS | Writing Exemplification |  | Look at Enquiry books (Priv 3 + 2)
LEAF Governance |  | FGB 3.3.25 @ 6:15pm
Term 5 | Wk 1: 22.4.25 | Wk 2: 28.4.25 | Wk 3: 5.5.25 | Wk 4: 12.5.25 SATs Week | Wk 5: 19.5.25 |  |  |  | T5 Priority Milestones: | T5 Impact
Priority 1: Vision - Further embed a culture of high expectations and challnege so that pupils deomnstrate high levels of resilience and intrinsic motivation |  | Introduce shifting the dial with staff. | [6 empty] | End of T61A: Mission Leaders launch survey & complete action plan for 2025-26. 1B: Evaluate impact of new lunchtime provision. 1B: TLaC: 1B Peer Critique: Trail peer critique in Art and Maths (YR-1, Y2-4, Y5-6). Codify as whole school approach linked to PGP. 1D: Create attendance approach linked to school mission and positive narrative around attendance
Priority 2: Writing - Further develop the teaching of writing so that more children meet or exceed the expected standard |  | Introduce shifting the dial with staff. | [6 empty] | End of term 6 Fidelity: • All teachers are confident in live modelling throughout non-fiction units of work • All teachers are confident in using assessment to identify children’s strengths and next steps, and are using this information to adapt and target teaching • EYFS and Y1 teachers are using assessments to identify when children are ready to move into more independent composition • Y6 teachers are providing opportunities for all children to revise their writing in line with grammar expectations Acceptability: • All teachers are following the non-fiction progression document and using this to plan and teach units of work Reach: • All children are being taught to their ability and next steps to ensure progress for all • All pupils are applying grammar into their independent non-fiction writing • All pupils in EYFS and Y1 are applying transcriptional skills with growing independence, moving towards composition for children who are ready • All Y6 pupils are regularly revising their writing
Priority 3: Curriculum - Refine the remaining foundation subjects so that pupils can retain, recall and apply knowledge across all subjects. | [8 empty] | End of term 6 Fidelity: - Across both Key Stages, Spark yard for Music and progression structure for DT are embedded and lessons are taught in a codified manner - All teachers using the assessment models (knowledge notes, concept cartoons, vocabulary) and identified gaps and addressing gaps with Indvidual pupils. Acceptability: - All staff teach lessons throughout the wider curriculum using the progression maps and codification - All pupils have visited a place of worship/visitor from a religious group has visited school. - All teachers are using knowledge notes in History, Geography and Science to ensure children retain core knowledge and key vocabulary in each lesson. Milestone: - Subject leaders making full use of assessment in order to monitor and refine provision in their subject areas
School Improvement Priority 1B: Disadvantaged children make the same progress as their peers in maths | [8 empty] | Medium term: End of Term 6 1) Intervention plan in place and being used by all year groups Teachers are confident in identifying gaps and barriers for the next year 2) Children are explicitly using precise vocabulary within Maths lessons. 3) Children to be able to talk about how their learning has progressed through the unit
MAINTAINING / EMBEDDING ACTIONS:
MONITORING:
DATA/ PM/ PPM TASKS: | PPMs
EVENTS/ HR/ SITE:
STAFF MEETINGS | Writing - Compare planning with EG - Next steps for 5 children (EG) | Shifting the Dial (BH) | Trust Staff Meetings (4 of 5) | PGP Peer Critique in Practical Subjects (EG) | Writing - Borderline Expected Moderation (BH)
SLT MEETINGS |  |  | Writing Book Look - handwriting and presentation
LEAF Governance |  | FGB 28.4.25 @ 6:15pm
Term 6 | Wk 1: 2.6.25 | Wk 2: 9.6.25 | Wk 3: 16.6.25 | Wk 4: 23.6.25 | Wk 5: 30.6.25 | Wk 6: 8.7.24 | Wk 7: 15.7.24 |  | T6 Priority Milestones: | T6 Impact
Priority 1: Vision - Further embed a culture of high expectations and challnege so that pupils deomnstrate high levels of resilience and intrinsic motivation | [8 empty] | 1A: Mission Leaders launch survey & complete action plan for 2025-26. 1B: Evaluate impact of new lunchtime provision. 1B: TLaC: 1B Peer Critique: Trail peer critique in Art and Maths (YR-1, Y2-4, Y5-6). Codify as whole school approach linked to PGP. 1D: Create attendance approach linked to school mission and positive narrative around attendance
Priority 2: Writing - Further develop the teaching of writing so that more children meet or exceed the expected standard | [8 empty] | End of term 6 Fidelity: • All teachers are confident in live modelling throughout non-fiction units of work • All teachers are confident in using assessment to identify children’s strengths and next steps, and are using this information to adapt and target teaching • EYFS and Y1 teachers are using assessments to identify when children are ready to move into more independent composition • Y6 teachers are providing opportunities for all children to revise their writing in line with grammar expectations Acceptability: • All teachers are following the non-fiction progression document and using this to plan and teach units of work Reach: • All children are being taught to their ability and next steps to ensure progress for all • All pupils are applying grammar into their independent non-fiction writing • All pupils in EYFS and Y1 are applying transcriptional skills with growing independence, moving towards composition for children who are ready • All Y6 pupils are regularly revising their writing
Priority 3: Curriculum - Refine the remaining foundation subjects so that pupils can retain, recall and apply knowledge across all subjects. | [8 empty] | End of term 6 Fidelity: - Across both Key Stages, Spark yard for Music and progression structure for DT are embedded and lessons are taught in a codified manner - All teachers using the assessment models (knowledge notes, concept cartoons, vocabulary) and identified gaps and addressing gaps with Indvidual pupils. Acceptability: - All staff teach lessons throughout the wider curriculum using the progression maps and codification - All pupils have visited a place of worship/visitor from a religious group has visited school. - All teachers are using knowledge notes in History, Geography and Science to ensure children retain core knowledge and key vocabulary in each lesson. Milestone: - Subject leaders making full use of assessment in order to monitor and refine provision in their subject areas
School Improvement Priority 1B: Disadvantaged children make the same progress as their peers in maths | [8 empty] | Medium term: End of Term 6 1) Intervention plan in place and being used by all year groups Teachers are confident in identifying gaps and barriers for the next year 2) Children are explicitly using precise vocabulary within Maths lessons. 3) Children to be able to talk about how their learning has progressed through the unit
MAINTAINING / EMBEDDING ACTIONS:
MONITORING:
DATA/ PM/ PPM TASKS:
EVENTS/ HR/ SITE:
STAFF MEETINGS |  | PGP - Finalise Whole school approach | Trust Staff Meetings (5 of 5) | Writing Moderation : Last look to support judgment
SLT MEETINGS
LEAF Governance |  | FGB 9.6.25 @ 6:15pm